## RFC v5
S. No. | Slide # | Topic
3 | 4/Costing sheet | Don’t see the costing for the 2 mirrors inside the wardrobes?
3.3, 5.5 | 5,12 | While the intent is to use handles, in this case the cabinet handle will hit the wall. Can you suggest an alternative such as profile?
3.5 | 6 | This should have been out of scope
5.3, 6.1 | 10,14 | Correct the laminate to Senzura White Oak Thud Crown F612 (veneer)
7.1 | 19 | There are 2 drawers in the second wardrobe from left. The drawing recognizes only one.
8 | 25-28 | I believe we need to remove GOLA from here. Loft laminate is TBD (off-white) and not Merino Beige
8.1 | Costing sheet | Any reason why the cost has increased considerably compared to R6?
8.1 | Costing sheet | We will need the bottom draw of CAB 1 to take more than 30kg. Hence pls propose the next higher options - 50kg/60kg?
8 | Costing sheet | Pls include "Horizontal partition in Loft / Intent to do horzontal partition with out vertical partition on sides " in the kitchen (as done for other room)
8 | 26 | CAB 2 has 3 draws
8 | 31 | Need Louvre for CAB 7 door also
8 | Costing sheet | I understand that additional granite will need to be procured. Cost not reflected?
8.3 | Costing sheet | Need to discuss if and what is required here?
8.14 | Costing sheet | Pls send us the catalog for hob, chimney, sink, faucet etc or connect with the dealers
9 | 55 | CAB2 (left side) = 450x300X2000, CAB3 (right side) = 300x300x1500 (or the max height possible at site) Socket needs to be in top corner of CAB 3 (right side cabinet)
9 | 55 | Both the cabinets need to be ~6" above the floor
How are any changes handled going forward?

## Costing R9
Design Build Inc (DBI) Web:www.designbuildinc.shop Facebook:https://facebook.com/dbi.bangalore Instagram: https://www.instagram.com/dbidesignbuildinc/ Winner of Best of Houzz Award for Design 2019, 2020 & 2021
INDICATIVE COSTING FOR COSTING DIRECTION GUIDANCE - FINAL COSTING AFTER DESIGN & MATERIAL FINALIZATION
Client | Mr Nitin & Ira Kapoor | Ref No: | R9
Project | SNN RAJ ETTERNIA | Date | 28.10.2021
Contact | Anup George, Mob: 99000 13580 , Email: anup.george@designbuildinc.in / George Mathew, Mob: 80951 80241, Email: george@designbuildinc.in
Sn | Item Description | Amount | Sub Total
1 | Foyer
1.1 | New door in front of existing door – Flush door in Veneer - design to be finalized | 0 |  | Out of scope
1.1A | Fixing of lock for the new door - Labour charge only and all materials to be provided by client | 1000 |  | Out of scope
1.2 | Video phone wiring in DBI scope - Laying of conduit pipe and cable details to be shared by video phone company - Indicative estimate and will be charged on actual quanitity. Will be charged at 200/Metre Phone model and installation to be in client scope and to be done with phone company technician | 10000 |  | Out of scope
1.3 | Foyer storage (Costing in veneer plus melamine polish ) Base unit 4’6” X 1’6” Side tall unit 1’6” X 9’ | 0 |  | Out of scope
1.4 | Foyer storage unit cushion - Base unit 3’6” X 1’ 6” / Wall mount unit (Back panel to be done in Plywood) / Cushion for back panel unit | 14125 |  | Out of scope
1.5 | Console unit (Costing in veneer plus melamine polish ) - 3’6” X 2’6” | 0 |  | Out of scope
1.6 | Electrical (Cost for electrical wiring work, fixture cost not included) - Corner pendent light 1 Nos / Wall light 1 nos | 3500 |  | Out of scope
1.7 |  |  | 28625
2 | Formal living
2.1 | Partition - (Costing in Veneer) - Jamping as per design 10’ 6” wide, height 9’ - Vertical members 7 Nos at 4” gap, height up to ceiling with base up to 2” - Vertical partition to level the fire sprinkler at ceiling 9” X 9’ | 0 |  | Out of scope
2.2 | Wall paneling as dummy beam extension up to family living wall- to be finished in Gyp board. Extension of beam in living room ending near to Powder room wall. ( Painting to be done by painting Vendor ) | 5000 |  | Out of scope
2.3 | Electrical (Cost for electrical wiring work, fixture cost not included) - Surface mount ceiling light 6 Nos - Reworking of ceiling light point for fixing light and chandelier (2 points) - Spotlight above artwork on both side walls – 2 nos | 15000 |  | Out of scope
2.3A | Supply and fixing of tiles in sit out - Approx 120 sq ft. Inclusive of materials, loading, transportattion, unloading, adhesives and wastage Tile of MRP 250/-- included in costing | 60000 |  | Out of scope
2.4 |  |  | 80000
3 | Pooja unit
3.1 | Jamping (Costing in Veneer) - Jamping as per design 3’ wide, height 7’ 6” | 0 |  | Out of scope
3.2 | Wall paneling with frosted glass finish - 2’6” wide 7’3” high | 13500
3.3 | Base unit - 4’ 9” X 6” (2 draws, to be fixed in L angle) | 0 |  | Include Veneer costing
3.4 | White marble top - 4’ 9” X 1’ 6” ( White marble available with Vendor of MRP 400 with single patty ) | 12000
3.5 | Electrical works - Cove lighting on both side of wall paneling - Inclusive of Pasolite strip lights | 10000
3.6 | Providing and fixing of 1 Hook in ceiling for hanging light | 1250
3.7 |  |  | 36750
4 | Storage Room
4.1 | 5’ + 3’ – L shape without doors - L shape storage with one slot for keeping ironing board - Indicative costing and final costing as per finalized design | 56000
4.2 |  |  | 56000
5 | Guest bedroom
5.1 | Wardrobe (Costing in Veneer) - 9’10” X 7’ + 2’ 2”high loft - (loft with lift-up mechanism) | 156825
5.2 | Add toe tray below the sliding door - 3.5K Per tray - 3 Nos considered in costing - Hettich channels. ~6" clear storage space | 10500
5.3 | Toilet top storage unit with mirror 1’6” X 2’ plus 9" x 2 feet open storage | 8250
5.4 | Toilet floor beading - double patty in Black Granite - , to separate between dry and wet area. - 1500/rft - Indicative estimate and will be as per actual measurements | 6000 |  | This is 2 ft in length now
5.5 | Providing and fixing of Toilet fixed glass partition in toughened glass - 7ft Saint Gobain toughened glass | 0
5.5 | Wall treatment in Brick finish - 6’ wide 9’ high Brick polish - not included in costing and if needed to be done by painting Vendor | 0
5.6 | Mirror inside wardrobe door - 2 Nos | 5950
5.7 | Electrical (Cost for electrical wiring work, fixture cost not included) - Surface mounted ceiling light 2 nos, hanging light 1 nos, wall light 2 nos, reworking of ceiling fan position | 13500 |  | Out of scope
5.8 |  |  | 201025
6 | Powder Room
6.1 | Under counter cabinet with side draw and door on both sides, center to have only door (no cabinet) width 3’ 2” X 1’7” (height) | 10000
6.2 |  |  | 10000
7 | Office room
7.1 | Wardrobe 6’ X 6’ 3" sliding wardrobe with normal swing loft doors on top - 2 drawers with locks/3ft (loft with lift-up mechanism) - IN VENEER | 103250
7.2 | Toe tray below wardrobe - Add toe tray below the sliding door - 3.5K Per tray - 2 Nos considered in costing - - IN VENEER | 7000
7.3 | Study table - No: 1 - 3’ 10” wide with top storage and loft above plus Credeza storage 1’6” X 2’5” below study table - with casters (loft with lift-up mechanism) Wall paneling with write on laminate - - IN VENEER | 48000
7.5 | Toilet beading 62” - double patty in Black Granite - , to separate between dry and wet area. - 1350/rft | 6975
7.6 | Toilet top storage unit with mirror 1’6” X 2’ plus 9" x 2 feet open storage | 8250
7.6A | Under counter cabinet - 2'2" x 1'7" | 7500
7.7 | Electrical - Wall lights above bed back 2 nos / Ceiling lights 2 nos / (Cost for electrical wiring only, fixtures not included) / Cost for ceiling fan position rework if required / Task lighting for study table 1 and 2 / 3 nos 5 Amp point each of study table 1 and 2 PLUS 5A for Printer, USB Charger socket | 22500
7.8 |  |  | 203475
8 | Kids’s room
8.1 | Wardrobe 6’ X 7’ sliding wardrobe with normal swing loft doors on top (loft with lift-up mechanism) - - IN VENEER | 103250
8.2 | Toe tray below wardrobe - Add toe tray below the sliding door - 3.5K Per tray - 2 Nos considered in costing | 7000
8.5 | Electrical - Wall lights above bed back 2 nos / Ceiling lights 2 nos / (Cost for electrical wiring only, fixtures not included) Cost for ceiling fan position rework if required / 3 nos 5 Amp point each of study table 1 | 11000 |  | Out of scope
8.6 | Toilet beading 62” - double patty in Black granite - , to separate between dry and wet area. - 1350/rft | 6975
8.7 | Toilet top storage unit with mirror 1’6” X 2’ plus 9" x 2 feet open storage | 8250
8.8 |  |  | 136475
9 | Master Bedroom
9.1 | L shape sliding wardrobe till ceiling - 14’ X 7. Wardrobe area and loft area to be covered with sliding shutters ( With Niche storage unit 9” X 7’ ) ( Aristo series, since L shaped wardrobe is coming ) | 280500 |  | Depending upon design finalization
9.2 | Toe tray below wardrobe - Add toe tray below the sliding door - 3.5K Per tray - 4 Nos considered in costing | 14000
9.3 | Dresser unit - 1’6” X 7’6” / Side storage unit 9” X 7’6” PLUS LOFT | 29000
9.5 | Electrical - Wall lights above bed back 2 nos / Ceiling lights 3 nos / (Cost for electrical wiring only, fixtures not included) Cost for ceiling fan position rework if required SHIFTING OF 3 nos 5 Amp point each above dresser unit (Bedroom) 1 nos 5 amp unit above dresser unit (Walkin wardrobe) PLUS 1 WALL AND 2 CEILING LIGHT | 19500
9.6 | Toilet beading 6’ - double patty in Black Granite - , to separate between dry and wet area. - 1350/rft | 8100 |  | This is nearly 2.5 to 3ft now
9.8 | Under counter cabinet two side draws, doors and center door without cabinet 6’ X 1’7” | 18000
9.9 | Toilet top storage - Over counter storage on either side of the mirror - 3 FEET X 3 FEET Mirror on centre and 1.5 feet x 3 feet cabinets on side | 21000
9.1 |  |  | 390100
10 | Kitchen
10.1 | Kitchen Cabinets - Top and bottom cabinets plus loft doors as per RFC drawings plus 2 nos of ledge on hob unit wall 14 Nos - 30 kg Hettich tandem boxes 1No Hettich or equivalent cutlery tray Hettich soft close hinges in Kitchen | 442800 |  | Why has this gone up so high compared to R6
10.2 | Plywood Partition finished in Gypsum Board as per design. 9’6”X 7’6” 4.5' x 7.5' ( Painting cost not included ) | 25312
10.3 | Additional wire baskets instead of plywood for Tandem boxes - 14 Nos x 3100 | 43400 |  | Pls relook based on our conversation today
10.4 | Toe tray below Kitchen cabinets - Add toe tray below the sliding door - 3.5K Per tray - 4 Nos considered in costing | 14000
10.5 | Chimney exhaust pipe covering | 7500
10.6 | Gas line works - From utility area to Hob and corrections to existing gas line | 15000
10.7 | Labour charge for removal of tiles and carting away of debris | 6000
10.7A | Plastering of wall, where tiles are removed & tile work with availabe tiles of MRP 75/- for civil rework area | 10000 |  | ?
10.8 | Plumbing rework for shifting existing points to accommodate dishwasher and sink position involving civil work | 10000
10.9 | Supply and fixing of Back spalsh tiles - Approx 75 sq ft. Inclusive of materials, loading, transportattion, unloading, adhesives and wastage Tile of MRP 250/-- included in costing | 37500
10.1 | Labour charge for Granite work with necessary cutting for Kitchen Sink, Hob and faucet. Counter = Approx 42 sq ft. | 10000
10.10A | Water cutting for Granite - Subject to feasibility on doing water cutting in available granite | 3500
10.11 | Electrical work - Fixture cost not included / Almost matching switch cost included Hob unit 2 nos 5 amp socket 2 Nos 5 amp socket on hob unit wall 2 Nos 5 amp socket on right side of hob unit wall Tall unit 2 nos 15 amp socket for microwave and OTG Fridge point Below sink – 1 nos 5amp and 1nos 15 amp Above sink wall 2 nos 5 amp socket Task lighting for all top cabinets (Approximate length - 23 running ft) - strip light cost also included Ceiling light point - 2 nos Ceiling fan point TBD | 38000
10.12 | Providing and fixing of Chimney , Hob, Faucet & Sink for kitchen . Chimney (Int code : RMB ) - Faber 60 cm 1350 m³/hr angular Kitchen Chimney (Hood Zenith FL SC BK 60, Filterless technology, Touch Control, Black) Hob (Int code : RMB) - Faber Hob 4 Italian Burner, Auto Electric Ignition, Glass Top (HOB Gas GB 724 MT) Black Sink - (Int code : RNM variant) - FS 3620 HM - Futura Hand carved series Faucet (Int code : RMB)- Fa -0bb tap -1no ( Futura ) | 60000 |  | How do we finalize on these items?
10.13 | Plumbing for under counter water purifier | 3000
10.14 | Coordination for fixing of under water purifer included in costing | 1
10.15 | Kit-August - 10% discount on Kitchen Cabinets * Valid for projects, where design advance is paid in August 2021 | -44280
10.16 |  |  | 681733
11 | Utility
11.1 | Storage above sink 3’6” X 2’6” | 24375
11.3 | Janitor closet 2.5’ X 7’ | 26250
11.3A | Removal of existing granite slab and refixing with L angle | 5000
11.3B | Plumbing rework for washing machine to new location | 5000
11.3C | Electrical rework - 2 Nos - 15A socket / 1 Nos - 5A socket for vaccum cleaner | 12500
11.3 D | Removal of existing tiles and carting away of debris | 6000
11.4C | Plastering if needed and fixing of new tiles - Approx 75 SFT . Tiles of MRP 75/- to be used | 22500
11.4 |  |  | 101625
12 | OTHER WORKS - INDICATIVE ESTIMATE
12.3 | Electrical shifting charge - 1500/ point - Final estimate as per finalized numbers. | 10000 |  | Out of scope
12.4 | Electrical new point - 4000/point - Final estimate as per finalized numbers. | 10000 |  | Out of scope
12.5 |  |  | 20000
13 | Design and Project management charges
13.1 | Design charges and Project management charges for the items mentioned in this costing sheet | 50000 | 50000
14 | TOTAL | 1995808 | 1995808
15 | Additional Discount @2.5% 0 - 10L - Discount @ 0.9% / 10L - 20L- Discount @ -1.8% / 20L - 30L - Discount @- 2.5% | -49895.2
16 | Total after additional discount | 1945912.8
17 | CGST @ 9 % | 175132.152
18 | SGST @ 9 % | 175132.152
19 | Discount @ 9 % | -175132.152
20 | Net Total with Tax after discount | 2121044.952
* All toe trays to have - Hettich channels. ~6 inch clear storage space
* While doing works , there is a chance of drilling through concealed water and electrical lines and if this occurs, the repair charge will be extra
GENERAL TERMS & CONDITIONS
1 | Current GST rates are at 18%
2 | All items included in this costing sheet will only be executed in site. If any item is not executed in site due to practical difficulty, unavailability or other reasons, that amount will be refunded.
3 | Any items not included in this costing sheet will not be done at site, even though, it was discussed or shown in presentation.
4 | Power supply to be provided free at site.
5 | Dimensions shown are indicative and minor changes can happen during site execution.
6 | Indicative estimate and final estimate as per finalized design and materials.
7 | All works will be under free service for 2 years from handing over date.
8 | Service calls to start after clearing final payments.
9 | Any charges to be paid to apartment association / other authorities for doing work should be paid by the client.
10 | CNC & Other detailing work like inserts will be charged extra.
11 | Payment Terms 1. 3% of estimated cost as advance to start designs. Design advance is non-refundable. | 63631.3486
| 50% after Design to start works | 1060522.476
| 44% after boxes are assembled in site. Shutter fixing for cabinets will start after this payment. | 933259.7789
| 3% on completion of full works. Reconciliation will be shared before this payment to arrive at the correct final figures | 63631.3486
12 | Boxes in Century Sainik plywood. Doors as per selected materials. Laminate of MRP 45/ sft Handles of MRP 300/- . Knobs of MRP - 100/- Inside laminate - white/offwhite laminate . Wardrobe boxes in MR Grade plywood and Kitchen boxes in BWP Plywood. Sliding wardrobe shutters in Aluminum profile and photos will be shared for better understanding . Sliding shutters will not have locks and internal drawers can have locks. All hardware items except lift ups from Hettich. If Hettich brand is not available at the time if execution, alternate brand to be used after consultation with Client. Soft close hinges only in Kitchen and normal hinges in other areas
13 | Painting of apartment after interior works is not included in costing. Painting and other touch up after electrical work, grill work and False ceiling painting is not included in costing and to be done with painting Vendor
14 | Rates valid till two weeks from date of estimate
15 | Ledges are not recommended for keeping heavy items
16 | Rates are for items in laminate finish. WPC board is available only in white color.
17 | Electrical and plumbing works not included in DBI scope of works
18 | During welding work, there will be sparks coming due to this process. We will doing covering of the area from our side, still there are chances of spark and black dust falling on uncovered area
19 | If the project is getting cancelled or delayed, design advance paid will not be refunded.
AP | Action Plan
AP1 | 3% design advance to be paid on or before August 31st, 2021
AP2 | Design process to start from September 1, 2021 and get completed by September 30, 2021
AP3 | Project work of listed items in costing sheet to start from October 1, 2021 and to get completed by December 31, 2021
AP4 | Revised costing as per finalized items to be given after the completion of 3D design and RFC drawings to start after approval of revised costing.
AP5 | Once design advance is paid, we will be starting a whatsapp group for easy communication during design phase, project phase and for after sales service All communication and reporting of the project will be happening through this whatsapp group
Bank account details : DESIGN BUILD INC, Current Account Number: 071383800000413, IFSC code: YESB0000713, YES BANK, Branch : Whitefield 2, BANGALORE
4.5
0.2037
0.5

## RFC v4
S. No | RFC Slide | Topic | Remarks
|  | The numbering between the costing sheet and RFC is lost. For ex 7.5 in RFC refers to electrical work and in costing sheet it refers granite slab in bathroom etc. | Pls see if the 2 documents can be maintained in sync
1.3 | 1 | Out of scope | Out of scope
2.1 | 2 | Out of scope | Out of scope
2.3 | 3 | Out of scope | Out of scope
3.1 |  | Specifications missing in RFC | Out of scope
3.3 | 4 | Do it in Veneer | UseSenzura Burnt Walnut F858 or Santos Rosewood- Horizontal (F993Hz)
4 | 5 | CAB 1 and CAB 3 seem to be incorrectly represented in the drawing. Also CAB1 & CAB3 to be adjacent | To be corrected
5 | 7 | Pls recognize the removable shelf in (all) the lofts | Discuss at site
5.3 | 8 | Pls recognize laminate code as Steel Frost (49946HGL SH V) | To be corrected
|  | Recognize the handle | Use a door front handle (No Gola)
5.6 | 9 | Out of scope | Out of scope
7.1 | 11 | Pls recognize the removable shelf in (all) the lofts | Discuss at site
7.6 | 15 | Pls recognize laminate code as Steel Frost (49946HGL SH V) | To be corrected
|  | Recognise the handle of top cabinet and bottom cabinet | Do not use Gola, use door front handles
8.1 | 17 | Pls recognize the removable shelf in (all) the lofts | Discuss at site
8.1 | 17 | Correct RFC to show Senzura White Oak Thud Crown F612 | To be corrected..it shows Merino Dawn Jagged
8.5 | 19 | Out of scope | Out of scope
9.1 | 23 | Wardrobe | Pls let me know if the attached design is feasible, else out of scope
9.3 | 26 | From the design, I understand that there is a light in the 9" open storage next to the Aristo. However this is not shown in the RFC | To be corrected
10 | 30 | The kitchen lower cabinet widths are not adding up. Can you pls relook at the dimensions The Wall A has length 99" but the cabinets are adding to 89". Cabinet widths on B&D also don’t add up | At site
| 30 | For the cabinets and lofts, the handle mentioned is GOLA/Push to Open? | Do not use gola. Lower Cab=Push to open/Door front handles, Upper=Push to Open, Loft=Push to open
| 30 | Pls use a 60kg capacity tandem box for the last draw of CAB1?
| 29 | Pls recognize the removable shelf in (all) the lofts | Discuss at site
| 30 | Recognize that CAB 3 & 5 has a removable shelf each | Will recognize
| 31 | CAB 11 - What does 600mm refer? Is it the length of the panel? Is it correct? | 600+600. To be corrected
| 32 | Recognize that all kitchen lofts are through and through with one removable shelf | Discuss at site
| 34 | CAB 13- RFC says "One door with glass and one door solid". It is a single door and should be recognized as a glass door | To be corrected
| 51 | The blue tiles on wall B are not in the middle (of the wall) | To be corrected
| 35 | CAB 6 : Top draw is cutlery, middle is saucer and last is Full Plates | To be corrected
| 34 | Design for the MW corner hasn’t come out correctly | L shaped corner open shelf with partition
| 35 | On slide 35, CAB 7 is repeating. One should be CAB8. | To be corrected
| 38 | I was of the opinion that all loft panels (as far as possible) will be hydraulic operated. | Combine 25,26,27 into 2 doors (hydraulic). CAB 21 is hydraulic
| 30 | Pls recognize the height of the lower cabinet drawers/boxes | To be included. Nitin to send the plate dimensions Note: Saucer 9", Plate 11"
|  | In the kitchen wherever there are 2 5AMP sockets, pls make 1 of those sockets as 15AMP | To be corrected
| 42 | These don’t look like Quadro channels? Also are these full plate & saucer & cutlery taken into scope/budget? | Sample to be shown
| 52 | Any reason why no tile has been proposed on the wall? | Use tiles till the bottom of the upper cabinet. Ignore the granite ledge if merging is an issue
| 55 | Will just a 3' partition behind the fridge be adequate? | Make the width 3'
11 | 58 | Do we need the middle partition in the broom closet. Also we don’t need a shelf on the right side | To be redesigned as L shaped closet without middle partition
|  | Electrical work for all rooms have been included in the RFC except for the Living and Dining? Also I don’t see any fan in the dining area in the design document.. | Out of scope

## RFC v3
General | Need to understand material and fittings used to confirm if requirements are correct
| Pls include electrical fitting on existing electrical points in scope. Ex wall lamps | Closed
S. No | Topic | Remarks
1.1 | Nitin to propose alternate design | Closed
| Need 1.1 ideally in wood | Closed
| It is assumed that the cost includes all reasonable accessories such as door frame, handles, latches etc (except the main lock set) | Closed
1.3 | The storage under the seating also needs louver doors and should look as an unified part of the vertical storage | Closed
| Pls show (using accessories or otherwise) how the storage under the seating can be best used for keeping shoes | Closed
| Reduce seat width to 3.5' | Closed
| How do we select the colour/fabric of the back and seat cushion? | Ongoing
| For the vertical storage pls show a single door till the top. Don’t need a separate loft. Do you think this will be ok? | Closed
| Need 2 drawers with lock in the vertical storage, rest of the space can be equal partitions with shelves | Closed
| In general, need the shelves that are removable. Pls call out where this is not the case. Also can we have (height) adjustable shelves | Closed
| Need polish/varnish (instead of white laminate) inside where ply maybe used | Closed
| Need 1.3 in wood | Closed
1.6 | What material and services are included in this? | Closed
2.1 | I presume installing the dummy on both sides will be done by DBI | Closed
| Need 2.1 in wood | Closed
| Pls propose a paint treatment on the wall between formal living and office room | Closed
2.3 | Bring CL1 and CL6 slightly to the right (along the center of the foyer section)? | Closed
| Pls provide a separate switch for WL1 and WL2 | closed
| Pls factor 2 additional Wall Lights on the powder room wall | Closed
| CL2 doesn’t appear under the SB's. Should S2 be CL 2,5? | Closed
| What material and services are included in this? | Closed
| We plan to put tiles on the formal living balcony walls. Can you include that in the RFC | Pls provide costing for putting tiles
3.1 | Need in wood | Closed
3.2 | Is the entire length of the mirror frosted, or is there some pattern on it? Can you pls propose some designs | Anup to share colour shade
3.3 | Need this in wood | Closed
3.5 | Need neutral white light everywhere (instead of warm white) | Closed
3.6 | I presume the hooks are for the 2 bells. The costing sheet says 'lights' | Closed
4 | The depth of the shelf needs to be 18" on the right wall and 22" on the front wall | Closed
| How are the shelves resting? Need these removable | Closed
| Need polish/varnish (instead of laminate) | Closed
| Why do we have CAB1 (and of the said dimensions). Can we avoid the partition? | Closed
| Where do we keep the ironing board here? | Closed
| CAB 1 - Width=6" with 3 partitions. Height of ironing board compartment = 5' | Closed
| Bring the current CAB3 adjacent to CAB1 ie switch location of CAB 2 and CAB3 | Closed
| CAB 2 & 3 should have 6 partitions both | Closed
| Need to discuss/evaluate electrical works - sockets,lights | Closed
| Can the bottom of the storage be open/floor is accessible? | Closed
5.1 | Need to revise the center & loft veneer to Senzura Twilight Call (F632) | Closed
| Need only 1 loft panel ideally (max 2). What brand of hydraulic mechanism are you proposing to use | Closed
| The (handle of the) leftmost cupboard should not hit into the wall | Closed
| Need to do away with the line in the middle of the wardrobes. | Closed
| Need locks on all 3 cupboards and the drawers | Closed
| It says "LOFT with lift up handle". What handle are we proposing? | Closed
| Pls add one removable shelf in all the lofts | Closed
| It will be good to see the fittings accounted for these cupboads | Closed
| The shelf need to be removable. | Closed
| Need polish/varnish (instead of white laminate) inside | Closed
| Had asked for a full length mirror to be included in the right and center cupboard (inner) door. Hope that is there | Closed
5.3 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width (as shown in picture) | Closed
| Use laminate Steel Frost (49946HGL SH V) | Closed
5.6 | What material and services are included in this? | Closed
| Need an additional ceiling light point near the corner of the front wall and bathroom wall | Closed
6.1 | The height of the cabinet below the slab to be 20". | Closed
| Give a removable shelf at the bottom of the center unit | Closed
| How will the doors be operated? (Are they push to open) | Closed
| Make provision for a dustbin to be fixed on the inner panel | Closed
| Use laminate Oyster Monochrome (21007) | Closed
7.1 | Need only 1 loft panel ideally. What brand of hydraulic mechanism are you proposing to use | Closed
| It says "LOFT with lift up handle". What handle are we proposing? | Closed
| Pls add one removable shelf in all the lofts | Closed
| It will be good to see the fittings accounted for these cupboads | Closed
| The shelf need to be removable. | Closed
| Need polish/varnish (instead of white laminate) inside | Closed
| Make the aristo panel completely mirror (remove the siam wood from the bottom). Also pls check if the profile can be steel colour (and not black) | Closed
| Use Champagne profiles for Aristo sliding wardrobes in all rooms | Closed
| Instead of white marker board (on the loft, sides and toetrays), lets use Rugby Woodburst 49953CFRSHV. Wil that look fine | Closed
| Instead of Rugby Woodburst, pls use White Oak Thud Crown F612 | Closed
7.3 | How will the printer be plugged to the power? We will need a power socket up also. | Closed
| Need a USB port to be included along with the power sockets. Also pls move the sockets to one side | Closed
| Hope the above shelves are removable as the printer has a flap that opens upwards | Closed
| Pls give wheels to the credenza. It will be good if (atleast the front) wheels have locks | Closed
| Pl use whiter marker board on the front wall, under the cabinet and the side between study table and cupboard | Closed
| Just confirming if the open shelves above the study table are made of glass? | Closed
| Can a metal plate be inserted behind the wall panelling so that magnets can be stuck there? | Anup to check
7.6 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width | Closed
| Below counter cabinet wxdxh= 25"x22"x20" | Closed
| Use laminate Steel Frost (49946HGL SH V) | Closed
8.1 | Need only 1 loft panel ideally. What brand of hydraulic mechanism are you proposing to use | Closed
| It says "LOFT with lift up handle". What handle are we proposing? | Closed
| Pls add one removable shelf in all the lofts | Closed
| It will be good to see the fittings accounted for these cupboads | Closed
| The shelf need to be removable. | Closed
| Need polish/varnish (instead of white laminate) inside | Closed
| Pls check if the profile can be steel colour (and not black) | Closed
| Use Champagne profiles for Aristo sliding wardrobes in all rooms | Closed
| Instead of white marker board (on the loft, sides and toetrays), lets useDawn Woodburst 44796RH. Wil that look fine | Closed
Instead of Dawn Woodburst, pls use White Oak Thud Crown F612
8.7 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width | Closed
| Use laminate Oyster Monochrome (21007) | Closed
9.1 | The carcass proposed is of a different design than what was shared. Any reason? Resharing the design here
| Pls add one removable shelf in all the lofts | Closed
| The shelf need to be removable. | Closed
| Need polish/varnish (instead of white laminate) inside | Closed
| Pls use champagne matt for profile | Closed
| We can use Siam Wood for the toe trays and the 9" compartment | Closed
9.3 | Make depth 12" | Closed
| Add a loft above | Closed
| In the main dresser, make it all equal sized shelves/compartments | Closed
| Handles? | Profile handle
| We will need padding between the dresser and the wall | Closed
9.4 | Cover only the inner walls of the bay window with wood | Closed
9.8,9.9 | Can we make the 2 wall cabinets as 18"x36" | Closed
| The below counter cabinet height at 20". Also give a removable shelf to the base of center cabinet | Closed
| Drawers on the right side may not be easily operated | Closed
Use laminate Oyster Monochrome (21007)
In the cabinets above the counter, swap the design of the bottom and top shelfs (assuming there are 3 shelfs)
10 | What is the height of the toe tray here? Acc to calculations it seems 2.8" - what will be the clear space then? | Closed
| CAB 8 height may not be 782mm. Similarly CAB 7 | Closed
Need a Louvre finish for panels of CAB7 & 8.
| Pls move the MW and Oven next to the fridge. The MW can rest of the counter with the oven over it | Closed
| We will need to revise the cabinets above the dishwasher as 2 x 3' wide cabinets | Closed
| Can you pls redesign CAB 13,14,15 therefore | Closed
| In the design ppt, pls show the close up of the MW/Oven corner | Closed
Pls suggest which sink (dimensions) is planned to be used? Can we meaningfully reduce width of cabinet 8 and adjust it in width of cabinet 7 & 9.
What is the design of the cabinet units - ex thali - big/small, bottom of units etc?
| Nitin (from Enzio) to propose alternate tiles and laminate | Closed
| Kitchen laminate - Monochrome Beige (21037) | Closed
| Cabinet 5 looks and needs to be bigger than cabinet 3. However the dimensions listed are the same? | Closed
| CAB 2 needs 3 drawers | Closed
| Cabinet 3 & 5 have a shelf each in the middle | Closed
| We did discuss this earlier and perhaps am restating. CAB 7 has a stabilizer & RO mounted. The door has a provision to hang a hand towel that falls inside the cabinet | Closed
| The toe press units need to be recognized in the RFC | Closed
| What is the height of the lofts? Pls add one removable shelf in all the lofts | Closed
| We can make the loft laminate colour the same as that of the main tile (off white) | Closed
| Pls keep only 1 column of the blue tiles in the center of either wall. The tile behind the hob are fine | Closed
| Pls recognize the plywood wall behind the refrigerator | Closed
11 | Pls redesign the utility | Done. Pls provide costing for civil/electrical work
11.1 | Revise dimensions of storage. Use laminate Penumbra Glass (49929)
11.3 | Revise dimensions of storage to 2.5'x6.5'. Use laminate Penumbra Glass (49929)
Nitin to share design of broom closet

## RFC v2.1
General | Need to understand material and fittings used to confirm if requirements are correct
S. No | Topic | Remarks
1.1 | Nitin to propose alternate design
Need 1.1 ideally in wood
1.3 | The storage under the seating also needs louver doors and should look as an unified part of the vertical storage | Closed
Pls show (using accessories or otherwise) how the storage under the seating can be best used for keeping shoes
Reduce seat width to 3.5'
How do we select the colour/fabric of the back and seat cushion?
| For the vertical storage pls show a single door till the top. Don’t need a separate loft. Do you think this will be ok? | Closed
| Need 2 drawers with lock in the vertical storage, rest of the space can be equal partitions with shelves | Just confirming if drawers have locks
| In general, need the shelves that are removable. Pls call out where this is not the case. Also can we have (height) adjustable shelves | Closed
| Need polish/varnish (instead of white laminate) inside where ply maybe used | Closed
| Need 1.3 in wood | Closed
1.6 | What material and services are included in this? | Closed
2.1 | I presume installing the dummy on both sides will be done by DBI | Closed
Need 2.1 in wood
Pls propose a paint treatment on the wall between formal living and office room
2.3 | Bring CL1 and CL6 slightly to the right (along the center of the foyer section)? | Closed
| Pls factor 2 additional Wall Lights on the powder room wall | Closed
| CL2 doesn’t appear under the SB's. Should S2 be CL 2,5? | Closed
| What material and services are included in this? | Closed
We plan to put tiles on the formal living balcony walls. Can you include that in the RFC
3.1 | Need in wood
3.2 | Is the entire length of the mirror frosted, or is there some pattern on it? Can you pls propose some designs
3.3 | Need this in wood
3.5 | Need neutral white light everywhere (instead of warm white) | Closed
3.6 | I presume the hooks are for the 2 bells. The costing sheet says 'lights' | Need only 1 bell (on the right side)
4 | The depth of the shelf needs to be 18" on the right wall and 22" on the front wall | Closed
| How are the shelves resting? Need these removable | Closed
| Need polish/varnish (instead of laminate) | Closed
| Why do we have CAB1 (and of the said dimensions). Can we avoid the partition? | Closed
Where do we keep the ironing board here?
| Need to discuss/evaluate electrical works - sockets,lights | Closed
Can the bottom of the storage be open/floor is accessible?
5.1 | Need to revise the center & loft veneer to Senzura Twilight Call (F632) | Closed
| Need only 1 loft panel ideally (max 2). What brand of hydraulic mechanism are you proposing to use | Closed
| The (handle of the) leftmost cupboard should not hit into the wall | Closed
| Need to do away with the line in the middle of the wardrobes. | Closed
| Need locks on all 3 cupboards and the drawers | Closed
| It says "LOFT with lift up handle". What handle are we proposing? | One slide shows handles on the loft panel?
| It will be good to see the fittings accounted for these cupboads | Closed
| The shelf need to be removable. | Closed
| Need polish/varnish (instead of white laminate) inside | Closed
| Had asked for a full length mirror to be included in the right and center cupboard (inner) door. Hope that is there | Closed
5.3 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width (as shown in picture) | Closed
Use laminate Steel Frost (49946HGL SH V)
5.6 | What material and services are included in this? | Closed
Need an additional ceiling light point near the corner of the front wall and bathroom wall
6.1 | The height of the cabinet below the slab to be 20". | Closed
| Give a removable shelf at the bottom of the center unit | Closed
How will the doors be operated? (Are they push to open)
Make provision for a dustbin to be fixed on the inner panel
Use laminate Oyster Monochrome (21007)
7.1 | Need only 1 loft panel ideally. What brand of hydraulic mechanism are you proposing to use | Closed
| It says "LOFT with lift up handle". What handle are we proposing? | Closed
| It will be good to see the fittings accounted for these cupboads | Closed
| The shelf need to be removable. | Closed
| Need polish/varnish (instead of white laminate) inside | Closed
| Make the aristo panel completely mirror (remove the siam wood from the bottom). Also pls check if the profile can be steel colour (and not black) | Closed
Use Champagne profiles for Aristo sliding wardrobes in all rooms
| Instead of white marker board (on the loft, sides and toetrays), lets use Rugby Woodburst 49953CFRSHV. Wil that look fine | Closed
Instead of Rugby Woodburst, pls use White Oak Thud Crown F612
7.3 | How will the printer be plugged to the power? We will need a power socket up also.
Need a USB port to be included along with the power sockets. Also pls move the sockets to one side
| Hope the above shelves are removable as the printer has a flap that opens upwards | Closed
Pls give wheels to the credenza. It will be good if (atleast the front) wheels have locks
Pl use whiter marker board on the front wall, under the cabinet and the side between study table and cupboard
Can a metal plate be inserted behind the wall panelling so that magnets can be stuck there?
7.6 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width
Below counter cabinet wxdxh= 25"x22"x20"
Use laminate Steel Frost (49946HGL SH V)
8.1 | Need only 1 loft panel ideally. What brand of hydraulic mechanism are you proposing to use | Closed
| It says "LOFT with lift up handle". What handle are we proposing? | Closed
| It will be good to see the fittings accounted for these cupboads | Closed
| The shelf need to be removable. | Closed
| Need polish/varnish (instead of white laminate) inside | Closed
| Pls check if the profile can be steel colour (and not black) | Closed
Use Champagne profiles for Aristo sliding wardrobes in all rooms
| Instead of white marker board (on the loft, sides and toetrays), lets useDawn Woodburst 44796RH. Wil that look fine | Closed
Instead of Dawn Woodburst, pls use White Oak Thud Crown F612
8.7 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width
Use laminate Oyster Monochrome (21007)
9.1 | The carcass proposed is of a different design than what was shared. Any reason? Resharing the design here
The shelf need to be removable.
| Need polish/varnish (instead of white laminate) inside | Closed
| Pls use champagne matt for profile | Closed
| We can use Siam Wood for the toe trays and the 9" compartment | Closed
9.3 | Make depth 12" | Closed
Add a loft above
| In the main dresser, make it all equal sized shelves/compartments | Closed
Handles?
| We will need padding between the dresser and the wall | Closed
9.4 | Cover only the inner walls of the bay window with wood | Closed
9.8,9.9 | Can we make the 2 wall cabinets as 18"x36" | Closed
| The below counter cabinet height at 20". Also give a removable shelf to the base of center cabinet | Closed
| Drawers on the right side may not be easily operated | Closed
Use laminate Oyster Monochrome (21007)
10 | What is the height of the toe tray here? Acc to calculations it seems 2.8" - what will be the clear space then?
CAB 8 height may not be 782mm. Similarly CAB 7
Need a Louvre finish for panels of CAB7 & 8.
Pls move the MW and Oven next to the fridge. The MW can rest of the counter with the oven over it
We will need to revise the cabinets above the dishwasher as 2 x 3' wide cabinets
Can you pls redesign CAB 13,14,15 therefore
In the design ppt, pls show the close up of the MW/Oven corner
Pls suggest which sink (dimensions) is planned to be used? Can we meaningfully reduce width of cabinet 8 and adjust it in width of cabinet 7 & 9.
What is the design of the cabinet units - ex thali - big/small, bottom of units etc?
Nitin (from Enzio) to propose alternate tiles and laminate
Kitchen laminate - Monochrome Beige (21037)
11 | Pls redesign the utility
11.1 | Revise dimensions of storage. Use laminate Penumbra Glass (49929)
11.3 | Revise dimensions of storage to 2.5'x6.5'. Use laminate Penumbra Glass (49929)

## Sheet4
Cabinet | Unit | Width x Depth x height [mm]
CAB 1 | 3 Nos Pot & Pan | 1050 x 600 x 782 | 41.3386 | 31.9184
CAB 2 | 2 Nos Pot & Pan | 525 x 600 x 782 | 20.6693
CAB 3 | Corner cabinet | 700 x 600 x 882 | 27.5591 | 34.7244 | 2.806
CAB 4 | 3 Nos Pot & Pan | 900 x 600 x 782 | 35.4331
CAB 5 | Corner cabinet | 700 x 600 x 882 | 27.5591
CAB 6 | 3 Nos Pot & Pan | 600 x 600 x 782 | 23.622
CAB 7 | Double door – Sink unit | 725 x 600 x 782 | 28.5433
CAB 8 | 2 Nos Pot & Pan | 600 x 600 x 782 | 23.622
| CAB1, CAB3 | Pots & Pans | Lids
| CAB6 | Cutlery
| CAB2 | Plastic containers | Lids
| CAB6 | Full plates
| CAB1 | Masala
Glass Bowls
Atta
| CAB2 | Chakla, belan
| CAB5 | Onion, Potato
Mixer & Accessories
| CAB6 | Quarter Plates, Katoris
Glasses, Cups

## RFC v1
General | Need to understand material and fittings used to confirm if requirements are correct
S. No | Topic | Remarks
1.1 | Nitin to propose alternate design | Done
Need 1.1 ideally in wood
1.3 | The storage under the seating also needs louver doors and should look as an unified part of the vertical storage
Pls show (using accessories or otherwise) how the storage under the seating can be best used for keeping shoes
How do we select the colour/fabric of the back and seat cushion?
For the vertical storage pls show a single door till the top. Don’t need a separate loft. Do you think this will be ok?
Need 2 drawers with lock in the vertical storage, rest of the space can be equal partitions with shelves
In general, need the shelves that are removable. Pls call out where this is not the case. Also can we have (height) adjustable shelves
Need polish/varnish (instead of white laminate) inside where ply maybe used
Need 1.3 in wood
1.6 | What material and services are included in this?
2.1 | I presume installing the dummy on both sides will be done by DBI
Need 2.1 in wood
2.3 | Bring CL1 and CL6 slightly to the right (along the center of the foyer section)?
Pls factor 2 additional Wall Lights on the powder room wall
CL2 doesn’t appear under the SB's. Should S2 be CL 2,5?
What material and services are included in this?
3.1 | Need in wood
3.2 | Is the entire length of the mirror frosted, or is there some pattern on it? Can you pls propose some designs
3.3 | Need this in wood
3.5 | Need neutral white light everywhere (instead of warm white)
3.6 | I presume the hooks are for the 2 bells. The costing sheet says 'lights'
4 | The depth of the shelf needs to be 18" on the right wall and 22" on the front wall
How are the shelves resting? Need these removable
Need polish/varnish (instead of laminate)
Why do we have CAB1 (and of the said dimensions). Can we avoid the partition?
Where do we keep the ironing board here?
Need to discuss/evaluate electrical works - sockets,lights
5.1 | Need to revise the center & loft veneer to Senzura Twilight Call (F632)
Need only 1 loft panel ideally (max 2). What brand of hydraulic mechanism are you proposing to use
The (handle of the) leftmost cupboard should not hit into the wall
Need to do away with the line in the middle of the wardrobes.
Need locks on all 3 cupboards and the drawers
It says "LOFT with lift up handle". What handle are we proposing?
It will be good to see the fittings accounted for these cupboads
The shelf need to be removable.
Need polish/varnish (instead of white laminate) inside
Had asked for a full length mirror to be included in the right and center cupboard (inner) door. Hope that is there
5.3 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width (as shown in picture)
5.6 | What material and services are included in this?
6.1 | The height of the cabinet below the slab to be 20".
Give a removable shelf at the bottom of the center unit
7.1 | Need only 1 loft panel ideally. What brand of hydraulic mechanism are you proposing to use
It says "LOFT with lift up handle". What handle are we proposing?
It will be good to see the fittings accounted for these cupboads
The shelf need to be removable.
Need polish/varnish (instead of white laminate) inside
Make the aristo panel completely mirror (remove the siam wood from the bottom). Also pls check if the profile can be steel colour (and not black)
Instead of white marker board (on the loft, sides and toetrays), lets use Rugby Woodburst 49953CFRSHV. Wil that look fine
7.3 | How will the printer be plugged to the power? We will need a power socket up also.
Need a USB port to be included along with the power sockets
Hope the above shelves are removable as the printer has a flap that opens upwards
Pls give wheels to the credenza. It will be good if (atleast the front) wheels have locks
Can a metal plate be inserted behind the wall panelling so that magnets can be stuck there?
7.6 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width
Below counter cabinet wxdxh= 25"x22"x20"
8.1 | Need only 1 loft panel ideally. What brand of hydraulic mechanism are you proposing to use
It says "LOFT with lift up handle". What handle are we proposing?
It will be good to see the fittings accounted for these cupboads
The shelf need to be removable.
Need polish/varnish (instead of white laminate) inside
Pls check if the profile can be steel colour (and not black)
Instead of white marker board (on the loft, sides and toetrays), lets useDawn Woodburst 44796RH. Wil that look fine
8.7 | Behind mirror storage of dimensions wxdxh=18"x5"24". And additional storage on its left of 9" width
9.1 | The carcass proposed is of a different design than what was shared. Any reason? Resharing the design here
The shelf need to be removable.
Need polish/varnish (instead of white laminate) inside
Pls use champagne matt for profile
We can use Siam Wood for the toe trays and the 9" compartment
9.3 | Make depth 12" | 12"
Add a loft above
In the main dresser, make it all equal sized shelves/compartments
Handles?
We will need padding between the dresser and the wall
9.4 | Cover only the inner walls of the bay window with wood
9.8,9.9 | Can we make the 2 wall cabinets as 18"x36"
The below counter cabinet height at 20". Also give a removable shelf to the base of center cabinet
Drawers on the right side may not be easily operated

## Sheet3 (hidden)
Office bath
Below Sink | 25"x22"x20" | wxdxh
Above sink | Mirror | 24"x5"x24"
Extension
Powder
wxdxh | 37x21x20 | 12x12x12
Guest
Above sink | Mirror | 22x5x24
| Extension |  | 64260 | 257040
203490
Dresser | 18X12 (24)xtop
Master Bath
Below sink | 72x22x20 | 24x24x24
abve | 16x36x
bay | 26x74
8.5+4.5)x74
top | 70x28

## Master Bedroom
Inch | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 102 | 104 | 106 | 108 | 110 | 112 | 114 | 116 | 118 | 120 | 122 | 124 | 126 | 128 | 130 | 132 | 134 | 136 | 138 | 140 | 142 | 144 | 146 | 148 | 150 | 152 | 154 | 156 | 158 | 160 | 162 | 164 | 166 | 168 | 170 | 172 | 174 | 176 | 178 | 180 | 182
2 | LOFT | [58 empty] | LOFT | [11 empty] | LOFT
4
6
8
10
12
14
16
18
20
22
24 | [14 empty] | SHELF | [71 empty] | 9" open storage
26 | ROD | [21 empty] | ROD | [36 empty] | ROD | [11 empty] | ROD
28 | SHELF
30
32
34
36
38 | [14 empty] | SHELF
40
42
44
46
48
50
52 | [14 empty] | SHELF
54
56
58
60
62
64 | [14 empty] | DRAWER | [50 empty] | DRAWER
66 | DRAWER | [6 empty] | DRAWER | [14 empty] | ROD | [48 empty] | DRAWER | [7 empty] | DRAWER
68 | [22 empty] | What is the minimal yet meaningful size for this corner?
70
72
74 | SHELF | [64 empty] | SHELF | [5 empty] | SHELF
76 | [14 empty] | DRAWER
78
80
82
84
86
88 | SHELF | [13 empty] | SHELF | [50 empty] | SHELF | [5 empty] | SHELF
90
92
94
96
98
100
102
104 | SHOES | [58 empty] | SHOES
106
108
110
ARISTO: Brown tinted mirror (Full)
| Corner |  |  | #REF! | [19 empty] | 63.4286
#REF!
#REF!
188